## Cover
Confidentiality & Copyright
The information contained in this document is confidential and is submitted by Matt Raynes on the understanding that only the staff and consultants to whom it is addressed will use it. The contents of this document may not be disclosed in whole or in part to any other party without the prior written consent of Matt Raynes.
Validity of Information Herein
Matt Raynes has made every effort to ensure that all statements and information contained in this document are accurate but accepts no liability for any error or omission in the same.
Please contact us on the below contact details.
Matt Raynes - Campaign Team
Name | Account Director | Email
Name | SEO Account Manager | Email
Matt Raynes Additional Contacts

## OnBoard
| SEO TECHNICAL STRATEGY | SEO CONTENT STRATEGY | LINK ACQUISITION STRATEGY | NOTES | RESPONSIBLE | DUE DATE | COMPLETED
MONTH 1
| SEO Campaign Plan |  |  | Timeline and Campaign Outline | Matt Raynes | Date | Y/N
| Google Analytics + Search Console Access |  |  | Grant Matt Raynes access | Client Name | Date | N
| SEO Technical Audit |  |  | Technical audit of the site | Matt Raynes | Date | N
| Google Webmaster Tools Review |  |  | Google Webmaster Tools Analysis & Documentation | Matt Raynes | Date | N
| Google Analytics Review |  |  | Google Analytics Review including Tracking | Matt Raynes | Date | N
| XML sitemap |  |  | Provision of updated XML sitemap | Matt Raynes | Date | N
| Robots exclusion review |  |  | Review robots.txt requirements | Matt Raynes | Date | N
| Microformatting |  |  | Review Schema mark-up requirements | Matt Raynes | Date | N
| Site Speed Analysis |  |  | Review of page load times | Matt Raynes | Date | N
| Technical Scorecard |  |  | Scoring system based on all tech audits. Completed to ensure priority actions. | Matt Raynes | Date | N
|  | Keyword Research & Insights |  | Keyword Research used to highlight keywords and find untouched areas | Matt Raynes | Date | N
| Website Taxonomy Audit | Website Taxonomy Audit |  | Evaluation of existing site category structure, with the outcome of a roadmap to improve current taxonomy. Includes top pageviews analysis and "Hero" page identification. | Matt Raynes | Date | N
|  | Ranking Report Set up & Initial Benchmark Report |  | Final set up for ongoing reporting | Matt Raynes | Date | N
|  | On-site Content Audit & Recommendations |  | Discussion on content production strategy and audit on requirements | Matt Raynes | Date | N
|  | Copywriting Guidelines |  | Provision of copywriting guidelines for future content development strategies | Matt Raynes | Date | N
|  | User Generated Content Audit |  | Evaluation of user-generated content e.g. reviews / UGC platforms. | Matt Raynes | Date | N
|  | Social Properties Audit |  | Evaluation of social channels with recommendations e.g. Facebook, Twitter, Google+ and LinkedIn. | Matt Raynes | Date | N
|  | Keyword Mapping |  | Target keywords document on based suitable pages onsite | Matt Raynes | Date | N
|  | Authority Content Audit |  | Evaluation of linkable assets including people, resources, tools, buyer's guides etc. | Matt Raynes | Date | N
|  | Content Scorecard |  | Scoring system based on all content audits. Completed to ensure priority actions. | Matt Raynes | Date | N
|  | Content Strategy Framework |  | Scoring system based on all content audits. Completed to ensure priority actions. | Matt Raynes | Date | N
|  |  | Backlink Risk Assessment | Review current backlink profile aimed at identifying any existing threats | Matt Raynes | Date | N
|  |  | Targeted Audience Audit |  | Matt Raynes | Date | N
|  |  | Stakeholder / Vendor Linking Audit | Identify all vendors (suppliers) who have "where to buy" pages, and find domains where client own or have a relationship with to find linking opportunities. | Matt Raynes/Client | Date | N
| Provision of SEO Issues Log |  |  | Document summarising all SEO issues identified during Strategy Phase | Matt Raynes | Date | N
| Site Health Check |  |  | Keyword Research used to highlight keywords and find untouched areas | Matt Raynes | Date | N
MONTH 2 | Technical Scorecard Updates |  |  | Scoring system based on all tech audits. Completed to ensure priority actions. | Matt Raynes | Date | N
|  | Keyword Research & Insights |  | Keyword Research used to highlight keywords and find untouched areas | Matt Raynes | Date | N
|  | Keyword Mapping |  |  | Matt Raynes | Date | N
|  | Title Tag and Meta Data Optimisation |  |  | Matt Raynes | Date | N
|  | Content Gaps Analysis |  |  | Matt Raynes | Date | N
|  | Content Scorecard Updates |  |  | Matt Raynes | Date | N
|  | On Page Content Development |  |  | Matt Raynes | Date | N
|  |  | Link Acquisition Tactic 1 |  | Matt Raynes | Date | N
|  |  | Link Acquisition Tactic 2 |  | Matt Raynes | Date | N
|  |  | Link Acquisition Tactic 3 |  | Matt Raynes | Date | N
|  |  | Link Acquisition Tactic 4 |  | Matt Raynes | Date | N
|  |  | Ongoing Backlink Monitoring | Identifying any potential threats | Matt Raynes | Date | N
| SEO Issues Log - Updates |  |  | Document summarising all SEO issues identified during Strategy Phase | Matt Raynes | Date | N
MONTH 3 | Monthly Reporting |  |  | Provision of a monthly report detailing all traffic and ranking increases and an overview on campaign activity | Matt Raynes | Date | N
| Site Health Check |  |  | Keyword Research used to highlight keywords and find untouched areas | Matt Raynes | Date | N
| Technical Scorecard Updates |  |  | Scoring system based on all tech audits. Completed to ensure priority actions. | Matt Raynes | Date | N
|  | Keyword Research & Insights |  | Keyword Research used to highlight keywords and find untouched areas | Matt Raynes | Date | N
|  | Keyword Mapping |  |  | Matt Raynes | Date | N
|  | Title Tag and Meta Data Optimisation |  |  | Matt Raynes | Date | N
|  | Content Gaps Analysis |  |  | Matt Raynes | Date | N
|  | Content Scorecard Updates |  |  | Matt Raynes | Date | N
|  | On Page Content Development |  |  | Matt Raynes | Date | N
|  |  | Link Acquisition Tactic 1 |  | Matt Raynes | Date | N
|  |  | Link Acquisition Tactic 2 |  | Matt Raynes | Date | N
|  |  | Link Acquisition Tactic 3 |  | Matt Raynes | Date | N
|  |  | Link Acquisition Tactic 4 |  | Matt Raynes | Date | N
|  |  | Ongoing Backlink Monitoring | Identifying any potential threats | Matt Raynes | Date | N
| SEO Issues Log - Updates |  |  | Document summarising all SEO issues identified during Strategy Phase | Matt Raynes | Date | N

## Campaign Plan
Issues | Sept | Oct | Nov
Title tags
Content alignment
Alt Tags
404s
Site Structure
Duped Pages
Page Load
Issues from the audits will be listed above along with the timeframe to complete all issues discovered in the SEO auditing process.

## Project Plan
Resource Allocation | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
| 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25
Audits
Technical | 2017-08-28: 8hrs; 2017-12-04: 8hrs
Content | 2017-08-28: 8hrs; 2017-12-04: 8hrs
Off Page | 2017-09-04: 8hrs; 2017-12-11: 8hrs
CRO | 2017-09-04: 8hrs; 2017-12-11: 8hrs
Editorial
Main Cat Pages | 2017-09-04: 8hrs; 2017-09-11: 8hrs; 2017-09-18: 8hrs
Sub Category Pages | 2017-09-18: 8hrs; 2017-09-25: 8hrs; 2017-10-02: 8hrs
Product Pages
Video
Optimisation
Seeding
Technical
Support/Review/Changes | 2017-07-03: AMP implementation; 2017-08-07: Meta Data
Off Page Campaign
Link Prospecting | 24hrs | 24hrs | 20hrs | 16hrs | 24hrs | 24hrs | 24hrs | 16hrs | 8hrs | 16hrs | 16hrs | 16hrs | 16hrs | 16hrs | 16hrs | 16hrs | 24hrs | 24hrs | 24hrs | 24hrs | 16hrs | 24hrs | 24hrs | 24hrs | 16hrs | 24hrs
BL Reclamation | 2017-07-10: 4hrs; 2017-07-24: 4hrs; 2017-08-14: 4hrs; 2017-08-28: 4hrs; 2017-09-11: 4hrs; 2017-09-25: 4hrs; 2017-10-09: 4hrs; 2017-10-23: 4hrs; 2017-11-06: 4hrs; 2017-11-20: 4hrs; 2017-12-04: 4hrs; 2017-12-18: 4hrs
Guest Post Prospecting | 2017-07-17: 2hrs; 2017-07-31: 2hrs; 2017-08-14: 2hrs
PR Production Distribution | 2017-07-03: 1hr; 2017-07-17: 1hr
Blog Post Writing | 2017-07-10: 4hrs; 2017-07-24: 4hrs; 2017-08-07: 4hrs; 2017-08-21: 4hrs
Authoritative Writing | 2017-08-07: 8hrs
Widget Dev/Concepts
Widget Monitoring
Social Media Competition
Blogger Outreach Campaigns | 2017-09-18: 16hrs; 2017-09-25: 16hrs
Infographic Development | 2017-10-02: 12hrs; 2017-10-09: 12hrs
Infographic Monitoring | 2017-10-16: 6hrs; 2017-10-23: 6hrs; 2017-11-06: 6hrs
Reporting
Monthly | 2017-07-31: 6hrs; 2017-08-28: 6hrs; 2017-09-25: 6hrs; 2017-10-30: 6hrs; 2017-11-27: 6hrs; 2017-12-25: 6hrs

## Content Outreach Strategy
Content Type | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
| 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25
Guest Post | bar: 2017-07-17; 2017-07-31; 2017-08-14; 2017-09-18; 2017-10-16
Blog Post | bar: 2017-07-10; 2017-07-24; 2017-08-07; 2017-08-21; 2017-09-04; 2017-09-18; 2017-10-02; 2017-10-23; 2017-11-13; 2017-11-27; 2017-12-11
Authoritative Post | bar: 2017-08-07; 2017-10-09; 2017-11-06
PR | bar: 2017-07-03; 2017-07-17; 2017-07-31; 2017-08-14; 2017-09-11; 2017-09-25; 2017-10-16; 2017-10-30 to 2017-11-06; 2017-11-20; 2017-12-04; 2017-12-18
Content should begin to focus on the January market, when searches begin to peak for people looking for a winter break. Content should be focused on this searcher intent and so should involve holidays, hotels and sunny winter resorts. Pieces should also consider linkability factors, why should a hotel in Tenerife link to one of our blog posts? Ensure we name some places so giving us the opportunity to outreach some of our blog posts rather than write a blog post with no marketing factors.
As the sector quietens it gives a good opportunity to develop a blogger outreach campaign. This could be an event that focuses on swimwear for the winter trip, and involve a catwalk event for a select group of bloggers. This could be arranged in a gated area of RevsDeCuba, perhaps? Similar things have been done, look at what competitors have done but plan it now for late November/December so the site feels the impact in January.
This is also a good time to look at content refreshes across the main pages along with the sub-category pages of the website.
PRs should be utilised with brand terms. Monitor brand terms using Google Alerts and find a hook back to our site for any newsworthy stories of brands we market.
Reviews from bloggers are a staple to this strategy and though reviews are not implemented into any time frame it's taken for granted that review placements will be consistently placed averaging anywhere between 10 - 16 placements a month. Busy months, like in the run-up to January, then review placements should be upped in November to ensure maximum impact occurs in january and then on from that month, moving forward.